## Tabelle1
Risk Category | Description | Risk Level (1-4) | Mitigation Strategy
Timeliness of Data | Delays in receiving annual data updates from OGP members. | 3 | Implement automated reminders and provisional updates with interim citizen-sourced data.
Data Quality and Completeness | Inaccurate or inconsistent data from multiple sources. | 4 | Enforce data validation protocols, standardize formats, and collaborate with data-producing organizations.
Funding Shortages | Insufficient funding for long-term maintenance of the platform. | 4 | Develop partnerships with international donors and explore public-private funding models.
Platform Downtime/Errors | System crashes or performance lags during peak usage. | 3 | Use scalable cloud infrastructure, perform regular stress testing, and monitor performance continuously.
Security Vulnerabilities | Risk of data breaches or cyberattacks. | 4 | Implement encryption, regular security audits, and comply with privacy regulations like GDPR.
Lack of Stakeholder Engagement | Limited involvement from key users like policymakers or NGOs. | 2 | Conduct user-centered design workshops and regular feedback sessions.
User Adoption Issues | Low adoption due to poor usability or lack of awareness. | 2 | Focus on UX/UI design, offer multilingual support, and run outreach campaigns to promote the platform.
Technology Obsolescence | Platform becomes outdated due to rapidly evolving technology. | 3 | Use modular, scalable architecture and plan for periodic technology upgrades.
Privacy and Compliance | Failure to comply with data privacy regulations. | 3 | Ensure compliance with GDPR and other standards, and adopt data protection best practices.
Integration Issues | Challenges integrating data from various sources. | 2 | Develop standardized data pipelines and use automated tools like Power Query for integration.